## Sheet1
Project [Flammable Blood]
Started: | March
Estimated Time of finnish: | 2020-01-01
Description: | Project for after school club 2019
Contributers (Details in Google Drive) | HB RYU and his unimportant quite useless friends
Note to self: |  | Log: | Remarks: | Check: | To Do (sequential): | Estimate Time(Hours) | Total(h)= | Works hours per day: | Estimate days: | 2019-04-06 로그 제작
2019-05-29 I know it's been tough. Please don't give up, they rely on you. |  | 2019-04-06 Log created | I seriously have no clue what to write in here. | 1 | Sprite mesh animation |  | 44.5 | 2 | 22 | 2019-04-07 총알 파편 시스템, 탄피, 창알 충돌 제작 완성
2019-06-03 Will be working till 15th of June (Exam coming up on July), that is about 2 weeks from now. |  | 2019-04-07 Bullet particle system, bullet shells, bullet collision |  | 1 | Particle FX (Basic) |  |  |  |  | 2019-04-08 다양한 무기 제작, 무기 수 제한
2019-07-06 Back to work, lazy piece o shit |  | 2019-04-08 Multiple weapons, weapon count limit |  | 1 | Weapons Mastering |  |  |  |  | 2019-04-09 장총 제작 중
|  | 2019-04-09 Hunting Rifle (Not finnished) |  | 1 | Multiple weapons |  |  |  |  | 2019-04-12 장총 제작 짜증나기 시작
|  | 2019-04-12 Hunting Rifle starting to piss me off |  | 1 | Experimental enemy |  |  |  |  | 2019-04-13 장총 제작 완성
|  | 2019-04-13 HuntingRifle finished (Maybe add a scope later?) |  | 1 | Damage stats calculation |  |  |  |  | 2019-04-15 샷건 제작 중
|  | 2019-04-15 Working on PointBlank Shotgun |  | 1 | Hand sprite mesh animation fix |  |  |  |  | 2019-04-16 샷건 제작 완성
|  | 2019-04-16 PointBlank Shotgun |  | 1 | Crouch |  |  |  |  | ~ 2019-05-09 무기 시스템 개선, 실험용 적 (경비, 공격, 절벽 감지), 바닥 택스쳐 제작
|  | ~ 2019-05-09 Weapon system fixes, Testing enemy (Patrol, chase, cliff detection), Ground textures |  | 1 | Moon walk (Hee hee) |  |  |  |  | 2019-05-09 바닥 택스쳐 개선, 점프 애니메이션 수정, 데미지 계산 제작 중
|  | 2019-05-09 Fixed Ground Textures, Jump animation fixed, Started working on damage stats calculation |  | 0.8 | Melee weapons (stun) |  |  |  |  | 2019-05-25 총알 사라지는 버그 수정, 데미지 스탯 계산, 기본적인 웅크리기 시스템
|  | 2019-05-25 Bullet disapearing bug fixed, Damage stats calculation, Basic crouch system |  | 1 | Jetpack |  |  |  |  | 2019-05-26 웅크리기 수정, 적 죽음 수정
|  | 2019-05-26 Updated crouch system, Updated enemy death |  | 1 | Elevators (Or as I like to call them, the british way, lifts.) |  |  |  |  | 2019-05-29 뒤로 걷기 제작 중
|  | 2019-05-29 Working on Michael Jackson |  | 1 | Enemies |  |  |  |  | ~ 2019-06-02 뒤로 걷기 완성, 전기 충격기 제작 중(어떤 이유인지 문제 계속 발생)
|  | ~ 2019-06-02 Moon walk finished, Trying to work on stun arm (Not working for some fucking reason) |  | 1 | Player health/Death system |  |  |  |  | 2019-06-03 전기 충격기 애니메이션
|  | 2019-06-03 Stun arm sprites & animation |  | 0.8 | Tiles | 1.5 |  |  |  | ~ 2019-06-05 전기 충격기 제작중, s예기치 못한 문제 발생;;
|  | ~ 2019-06-05 Working on stun arm, some unexpected problems |  | - | BackGround (+ Parallax) | 3 |  |  |  | 2019-06-06 전기충격기 거의 다 완성
|  | 2019-06-06 Stun arm almost finished |  |  | UI | 2.5 |  |  |  | 2019-06-07 전기충격기 어떤 문제 생겨서 제대로 장착이 안됨
|  | 2019-06-07 Stun system something went wrong..? Not equiping weapons properly |  |  | Sounds | 3 |  |  |  | 2019-07-04 전기 충격기 포기 ㅎ
|  | 2019-07-04 Gave up stun |  |  | Fuel system | 1 |  |  |  | ~2019-07-06 제트팩 완성, 앨리베이터 완성
|  | 2019-07-06 Elevator finnished |  |  | NPCs | 2.5
|  | ~2019-07-15 Working on new enemy AI |  |  | NPC Animation (Basic) | 3
|  | ~2019-8-17 New enemy AI finished, Drones |  |  | Dialogue System | 1.5
[5 empty] | Various Items (+ upgrade modules) and portals | 3.5
[5 empty] | Control panel | 4
[5 empty] | Basecamp (Lobby) | 4.5
[5 empty] | Particle FX (Advanced) | 2
[5 empty] | Level proggression system | 3
[5 empty] | Cleaning and mastering #1 | 2.5
[5 empty] | Boss | 4
[5 empty] | LEVEL 1-1 | 3