## Sheet1
Log: | Remarks: | Check: | To Do (sequential): | Estimate Time(Hours) | Total(h)= | Works hours per day: | Estimate days:
2019-04-06 Log created |  |  | Sprite mesh animation | 0.5 | 41.5 | 3 | 14
|  |  | Multiple weapons | 1.5
|  |  | Experimental enemy | 2.5
|  |  | Damage stats calculation | 2
|  |  | Melee weapons | 3
|  |  | Jetpack | 3.5
|  |  | Enemies | 4.5
|  |  | UI | 2.5
|  |  | NPCs | 2
|  |  | Dialogue System | 1.5
|  |  | Various Items (+ upgrade modules) and portals | 3.5
|  |  | Control panel | 4
|  |  | Basecamp (Lobby) | 4.5
|  |  | Level proggression system | 3
|  |  | Sounds | 3