## Sheet1
Log: | Remarks: | Check: | To Do (sequential): | Estimate Time(Hours) | Total(h)= | Works hours per day: | Estimate days:
2019-04-06 Log created |  | 1 | Sprite mesh animation |  | 55.5 | 3 | 19
2019-04-07 Bullet particle system, bullet shells, bullet collision |  | 1 | Particle FX (Basic)
2019-04-08 Multiple weapons, weapon count limit not set yet |  | 1 | Weapons Mastering | 1
|  | 0.8 | Multiple weapons | 2
|  |  | Experimental enemy | 3
|  |  | Damage stats calculation | 2
|  |  | Melee weapons | 3.5
|  |  | Jetpack | 3.5
|  |  | Enemies | 4.5
|  |  | Tiles | 3
|  |  | BackGround (+ Parallax) | 3
|  |  | UI | 2.5
|  |  | NPCs | 2.5
|  |  | NPC Animation (Basic) | 3
|  |  | Dialogue System | 1.5
|  |  | Various Items (+ upgrade modules) and portals | 3.5
|  |  | Control panel | 4
|  |  | Basecamp (Lobby) | 4.5
|  |  | Level proggression system | 3
|  |  | Sounds | 3
|  |  | Particle FX | 2.5