## Sheet1
Project [Flammable Blood]
Started: | March
Estimated Time of finnish: | 2020-01-01
Description: | Project for after school club 2019
Contributers (Details in Google Drive) | HB RYU and his unimportant quite useless friends
Note to self: |  | Log: | Remarks: | Check: | To Do (sequential): | Estimate Time(Hours) | Total(h)= | Works hours per day: | Estimate days:
2019-05-29 I know it's been tough. Please don't give up, they rely on you. |  | 2019-04-06 Log created | I seriously have no clue what to write in here. | 1 | Sprite mesh animation |  | 52.5 | 2 | 26
2019-06-03 Will be working till 15th of June (Exam coming up on July), that is about 2 weeks from now. |  | 2019-04-07 Bullet particle system, bullet shells, bullet collision |  | 1 | Particle FX (Basic)
|  | 2019-04-08 Multiple weapons, weapon count limit |  | 1 | Weapons Mastering
|  | 2019-04-09 Hunting Rifle (Not finnished) |  | 1 | Multiple weapons
|  | 2019-04-12 Hunting Rifle starting to piss me off |  | 1 | Experimental enemy
|  | 2019-04-13 HuntingRifle finished (Maybe add a scope later?) |  | 1 | Damage stats calculation
|  | 2019-04-15 Working on PointBlank Shotgun |  | 1 | Hand sprite mesh animation fix
|  | 2019-04-16 PointBlank Shotgun |  | 1 | Crouch
|  | ~ 2019-05-09 Weapon system fixes, Testing enemy (Patrol, chase, cliff detection), Ground textures |  | 1 | Moon walk (Hee hee)
|  | 2019-05-09 Fixed Ground Textures, Jump animation fixed, Started working on damage stats calculation |  | 0.5 | Melee weapons (stun) | 3.5
|  | 2019-05-25 Bullet disapearing bug fixed, Damage stats calculation, Basic crouch system |  |  | Jetpack | 3.5
|  | 2019-05-26 Updated crouch system, Updated enemy death |  |  | Elevators (Or as I like to call them, the british way, lifts.) | 2.5
|  | 2019-05-29 Working on Michael Jackson |  |  | Enemies | 6
|  | ~ 2019-06-02 Moon walk finished, Trying to work on stun arm (Not working for some fucking reason) |  | 0.5 | Tiles | 1.5
|  | 2019-06-03 Stun arm sprites & animation |  |  | BackGround (+ Parallax) | 3
[5 empty] | UI | 2.5
[5 empty] | Sounds | 3
[5 empty] | NPCs | 2.5
[5 empty] | NPC Animation (Basic) | 3
[5 empty] | Dialogue System | 1.5
[5 empty] | Various Items (+ upgrade modules) and portals | 3.5
[5 empty] | Control panel | 4
[5 empty] | Basecamp (Lobby) | 4.5
[5 empty] | Level proggression system | 3
[5 empty] | Particle FX | 2.5
[5 empty] | Cleaning and mastering #1 | 2.5