## Sheet1
[7 empty] | Estimated total work hours: | 24.1 | Estimated percentage: | 37.3444 | %
|  | Task logs V 2.0 |  |  |  |  | Total hours spent: | 9
Hours spent (day): | Date: | Log: | To do: | Check: | Estimate hours: | Hours spent (task):
| 2020-07-01 | Intro SFX, rain particles, simple items, etc | Rain sfx intro fade in | 1 | 0.5 | 0.2
1.5 | 2020-08-01 | RainSFX Intro vol/pan control, Intro start anim disable, intro level design, enemy stats update, enemy AI update etc | Intro start animation fix | 1 | 0.5 | 0.1
4 | 2020-09-01 | Intro title/credits display, soundtrack, box/bullet impact SFX etc | Intro props, lights/shadows | 1 | 0.7 | 0.5
1.5 | 1/13/2020 | Inventory finished, ammo display fixed, firearms audio improved | Intro tutorials | 1 | 1 | 0
2 | 1/16/2020 | UI objective pointer added, display debug cmd bug (line limit) needs fix | Box SFXs, bullet SFXs | 1 | 0.6 | 2
|  |  | Display debug cmd | 1 | 0.8 | 0.5
|  |  | Intro Title display | 1 | 0.5 | 0.5
|  |  | Intro soundtrack | 1 | 1.5 | 1
|  |  | Inventory fix | 1 | 1 | 1
|  |  | Inventory: item stats | 1 | 1.6 | 2.5
|  |  | Ammo display fix | 1 | 0.5 | 0.3
|  |  | Deployables display fix | 1 | 0.4 | 0.2
|  |  | Arrow guide | 1 | 1.2 | 1.5
|  |  | Display debug cmd SFX, character sequential typing display | 0 | 1
|  |  | Mastering #1 | 0 | 1.2
|  |  | NPCs | 0 | 1.6
|  |  | Dialogue system | 0 | 1
|  |  | NPCs animation | 0 | 2
|  |  | Intro -> Basecamp cutscene, Level managing | 0 | 2.5
|  |  | BaseCamp | 0 | 4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0